## Sheet1
Task | Dependencies | Number
Project Approval |  | 1
Database UML Construction | 1 | 2
Backend UML Construction | 1 | 3
Frontend UML Construction | 1 | 4
UML Review | 2,3,4 | 5
UML Approval | 5 | 6
Database construction | 6 | 7
File and Package Structure Implemented | 6 | 8
Populate Database with Fake Data | 7 | 9
Frontend Wireframe: Pick Prof/Lab | 8 | 10
Frontend Implementation: Pick Prof/Lab | 10 | 11
Frontend Wireframe: Display Prof Info | 11 | 12
Backend Implementation: Retrieve Prof Info |  | 13
Frontend Implementation: Display Prof Info | 12,13 | 14
Frontend Wireframe: Map Display | 14 | 15
Backend Implementation: Retrieve Map Info |  | 16
Frontend Implementation: Display Map | 15,16 | 17
Frontend Wireframe: Login | 17 | 18
Backend Implementation: Login/Session |  | 19
Frontend Implementation: Login | 18,19 | 20
Frontend Wireframe: IST Staff Landing View | 20 | 21
Frontend Implementation: IST Staff Landing View | 21 | 22
Frontend Wireframe: IST Staff Add Professor | 22 | 23
Backend Implementation: Add Professor |  | 24
Frontend Implementation: IST Staff Add Professor | 23,24 | 25
Frontend Wireframe: IST Staff Update Professor | 25 | 26
Backend Implementation: Update Professor |  | 27
Frontend Implementation: IST Staff Update Professor | 26,27 | 28
Frontend Wireframe: IST Remove Professor | 28 | 29
Backend Implementation: Remove Professor |  | 30
Frontend Implementation: IST Remove Professor | 30,31 | 31
Frontend Implementation: IST View Professor Info | 31 | 32
Frontend Wireframe: Mobile Map Display | 32 | 33
Backend Implementation: Map Link Generator |  | 34
Frontend Implementation: Mobile Map Display | 33,34 | 35
Stakeholder Dry Run | 35 | 36
Bug Fixes | 36 | 37
IST Student UAT | 37 | 38
Bug Fixes | 38 | 39
Stakeholder Approval | 39 | 40
Product Presentation (End of Class) | 40 | 41
FMS Begin Installation | 41 | 42
FMS End Installation | 42 | 43
Product Loaded on Raspberry Pi Browser | 43 | 44
Students Begin Use | 44 | 45